Indicator: Implement and evaluate 2009-12 SPS Technology Plan – specifically as it relates to the Smartboard Plan.

| ADULT ACTION INDICATORS Strategies | Person(s) Responsible | Staff Impacted by Strategy | Results Expected |
| --- | --- | --- | --- |
| Evaluate the benefit/cost value of Smartboards in the classroom. - Staff Survey - Walk-through – collect empirical data. Use ISTE or other self-designed tool. - Usage through online repair/inventory/usage system. - Observations (Informal, Formal) - Continued review of literature. - Professional Learning Program **Periodic assessments of data (Dec. 2009, April 2010, October 2010) | Virginia Hamm CIPL Director Principals Coordinators Media Staff Tech Committee Hedda Lettuce | Principals/Coordinators – to use online classroom observation system. | Survey results – Communicated through Monitoring Report / Budget Review |
| Ensure systematic, effective program to train teachers on use of Smartboards. - Basics Training for all teachers receiving SB - Train-the-Trainer program ($4995) - Design Webinar, online learning opportunities - Smartboard User Groups - Building-level advanced workshops **Hire .2 technology coach to provide just-in-time support, ongoing training, etc. | CIPL Director Tech. Coach Virginia Hamm |  | EZ-Traxx monitoring. Self-assessment. TEPL – observations Communicated through Monitoring Report / Budget Review |
| Provide centralized workspace to share resources/lessons developed for Smartboard. **Include all Coordinators/Principals in process of sharing “best practices”. | Virginia Hamm LMS Tech Coach Teachers |  | Rich collection of lessons, resources and “best practices” for the instructional use of the Smartboard. Communicated through Monitoring Report / Budget Review |
| Implement “Digital Educator” Blog to provide ongoing communication of “best practices”, research, available professional learning, UserGroup opportunities, etc. | Virginia Hamm Tech Coach |  | Increased awareness of types of instructional strategies that are supported through the use of Smartboard in the classroom. |